## Repo_Review
Finding | Current repository reality | Development decision
Repository | egcponcho/facturacion is accessible through the connected GitHub integration. | Use the connected repository as the source of truth instead of the earlier screen-only assumptions.
Branches | Only main and claude/bold-lovelace-iwx2wa were found. The Claude branch is 8 commits ahead of main and 0 behind. | Review/merge the current Claude work before starting the tariff refactor, or branch the refactor from that head.
Current stack | FastAPI + SQLAlchemy + Pydantic backend; Vue 3 + Vue Router + Vite frontend. The tariff engine itself is mostly pure JavaScript in frontend/src/clasificacion/motor.js. | Do not rewrite the whole platform. Refactor the classification engine and tariff data model incrementally.
Generic product model | Producto already stores a dynamic JSON ficha, suggested/approved code, analysis, status, version and country results through PartidaPais. | Keep Producto as the generic product/tariff-sheet aggregate. Normalize only the tariff configuration/rule layer.
Country results | PartidaPais already stores one country code per product and country. | Extend it with tariff version/source/evidence instead of replacing the concept.
Official SAC | The repo already contains SIECA-derived SAC files, legal notes, scripts to rebuild them and tests for the official base. | Preserve the ingestion scripts but version the imported datasets and stop mixing official data with inferred engine conditions.
Tariff structure | PartidaSAC only supports 4- and 6-digit nodes. IncisoNacional stores national code + JSON cond + prio. | Replace/augment this with a hierarchical TariffNode model and separate ClassificationRule/RuleCondition entities.
National code coupling | IncisoNacional.cond stores gender, age, footwear style, sleeve, etc.; priority is stored on the national code. | Move product conditions and priority out of the official national-code row. National code becomes official data only.
Dynamic form | FichaTecnica.vue is dynamic, but visibility comes from hard-coded ATTRS.aplica(), grupoTipo(), CAP_OK and product type arrays in motor.js. | Keep the UX but move visibility/requirements to Attributes + AttributeScope + Rules loaded from the backend.
Global search | The latest branch already adds frontend/src/busqueda.js and matching server normalization for multi-term, accent-insensitive search. | Do not rebuild this. Reuse it in tariff-tree, attributes, rules and import screens.
Any-product support | README describes 'Any other product', but CampoCategoria.vue only exposes the hard-coded TIPOS list and no generic any-product entry was found. | Treat the README statement as ahead of the implementation. Add a true generic/manual candidate path rather than another hard-coded category.
Chapter coverage | motor_meta.json currently has 29 chapter mappings. cargar_incisos_base() filters ACI national lines to those chapters before seeding. | The current database is not yet a full national-code catalogue for all SAC chapters. Chapter_Control and versioned ingestion should determine what is enabled.
Country digit rule | PaisArancel.digitos enforces one exact national-code length and guardar_inciso/importar_incisos reject other lengths. | Replace exact-length validation with configurable code schemas/precision rules; keep full_display_code and normalized_code.
Deletion/history | SAC and national codes can be physically deleted; replacement imports can delete a country's existing rows. | Published official rows must be archived/deactivated/versioned, not hard-deleted.
Bulk tariff import | Current tariff Excel import validates and writes directly; reemplazar deletes existing country codes before inserting. | Introduce staging → validate → diff → approve → publish for official tariff datasets.
Migrations | The app comments that production uses Alembic, but no Alembic files are present in the repository tree reviewed. | Add Alembic before the tariff schema refactor. Do not rely on create_all for production schema evolution.

## Branches
Branch | Head / status | Relevant conclusion
main | a9d1e251…; contains merged PR #18 | Stable baseline, but it does not contain the eight later Claude commits.
claude/bold-lovelace-iwx2wa | f67e2c72…; 8 commits ahead, 0 behind main | Current working branch. Includes global smart search, configurable lead-time steps, generic size scales, profile/preferences and normalization improvements.

## Current_Models
Current model/file | What it already provides | Keep / change
Producto | Generic product tariff sheet; dynamic ficha JSON; suggested/proposed/approved code; confidence; analysis; status; audit fields; ficha versions. | KEEP aggregate. Add classification dataset/version/evidence references.
PartidaPais | Country-specific code, DAI, status, source, manual flag. | KEEP concept. Add national tariff version/source/validity/regulation snapshot.
ProductoVersion | Closed tariff-sheet versions with copied data. | KEEP and extend to include classification dataset IDs and country snapshots.
PaisArancel | Country, exact digit count, MCCA flag, tax note, legal basis, active flag. | CHANGE exact digit count into configurable code format/precision rules; separate tax rules.
PartidaSAC | 4/6-digit SAC headings/subheadings. | MIGRATE/AUGMENT to TariffNode hierarchy with section/chapter/heading/HS6/SAC/national levels.
NotaSAC | RGI, section/chapter/subheading/complementary/explanatory notes with chapter scopes. | KEEP concept; add version/source/validity and stronger scope references.
IncisoNacional | Country national code + sub6 + cond JSON + priority + DAI + description/source. | SPLIT into NationalCode official data + ClassificationRule/RuleCondition.
PalabraClave / SinonimoMaterial | Learned product phrases and material synonyms. | KEEP. Generalize synonyms so they can apply to products, attributes, tariff nodes and options.
motor.js | Large rule engine with hard-coded product types, attributes, chapter compatibility, national-code scoring and descriptions. | DECOMPOSE. Keep pure functions where useful, move domain/rule metadata to DB/API.
FichaTecnica.vue | Good progressive tariff-sheet UX and composition editor. | KEEP UX. Render fields from backend configuration/candidate needs instead of hard-coded ATTRS.
ArancelesView.vue | Country/SAC/national-code/legal-note administration. | EXPAND into Tariff tree, Chapters, Notes, National codes, Regulations, Taxes, Attributes, Rules, Sources/Versions, Imports.

## File_Plan
File / area | Action | Specific implementation
backend/app/models.py | Refactor schema | Add TariffDataset/Version, TariffNode, ChapterControl, TariffSource, AttributeDefinition, AttributeOption, AttributeScope, ClassificationRule, RuleCondition, NationalCode, Regulation, TaxRule, ImportBatch/ImportRow. Preserve Producto/PartidaPais/ProductoVersion.
backend/app/schemas.py | Add contracts | Schemas for tree nodes, chapter bulk actions, attributes/options/scopes, rule builder, version/source CRUD, staging diff/publish and classification-session responses.
backend/app/services/aranceles.py | Split responsibilities | Move country/node/national-code CRUD to official-data services. Remove product conditions from national-code CRUD. Add versioned archive/deactivate semantics.
backend/app/services/productos.py | Preserve aggregate | Keep product/ficha workflow. Replace fixed OBLIGATORIOS and national-code condition selection with engine session output. Persist HS6 + SAC + evidence + country overlays.
backend/app/services/meta.py | Transition adapter | During migration, translate current motor_meta.json into Attribute/Option/Scope seed rows so existing footwear/apparel/accessory behavior remains.
backend/app/data/*.json | Version datasets | Treat current SIECA JSON files as immutable source snapshots; attach dataset/version/source metadata instead of loading them as anonymous seed data.
backend/scripts/sieca/* | Keep + harden | Retain extraction scripts, add source checksum/publication/version metadata and validation counts before publishing a new dataset.
backend/app/main.py | Migration safety | Stop depending on create_all for production evolution; wire Alembic migration execution/deployment procedure.
frontend/src/clasificacion/motor.js | Decompose | Move TIPOS, ATTRS, CAP_OK, national condition metadata and rule priorities out of the JS bundle. Keep reusable normalization/material parsing/description helpers where justified.
frontend/src/clasificacion/useClasificacion.js | Change engine bridge | Load engine configuration + create/update classification session; backend returns candidates, reasons, next attributes and country states.
frontend/src/components/ficha/FichaTecnica.vue | Data-driven fields | Render attribute controls by data type and scope; preserve composition UI; never erase a previous value just because a field becomes hidden.
frontend/src/components/ficha/CampoCategoria.vue | Generalize | Commercial domain/category becomes a searchable hint. Add Other/Generic path and support admin-defined domains/options.
frontend/src/views/ArancelesView.vue | Expand admin UI | New tabs and bulk operations. National code editor contains only official fields; rules get a separate visual builder.
frontend/src/busqueda.js | Reuse | Apply existing smart-search helper to tariff nodes, rules, attributes, sources and import-diff tables.
backend/tests/test_aranceles.py | Rewrite expectations | Remove tests that require product-condition columns in national-code templates or exact fixed country digit length. Add version/history/staging/rule tests.
New migrations | Required | Create Alembic baseline from current schema, then additive migrations; backfill existing IncisoNacional conditions into rules before dropping/deprecating cond/prio.

## Migration_Phases
Phase | Goal | Deliverable / exit criterion
0 | Stabilize branch | Merge or intentionally base the refactor on claude/bold-lovelace-iwx2wa; run existing tests/build before tariff changes.
1 | Add Alembic + dataset/version/source layer | No destructive reset required for production; current tables still work.
2 | Add ChapterControl + TariffNode alongside PartidaSAC | Current classifications continue; official tree can be browsed and chapters enabled/disabled.
3 | Add Attributes/Options/Scopes | Seed them from motor_meta.json and reproduce the existing dynamic footwear/apparel/accessory form.
4 | Add ClassificationRule/RuleCondition | Migrate IncisoNacional.cond/prio and key motor.js rules into data-driven records; keep compatibility adapter.
5 | Refactor FichaTecnica + classification session | Frontend no longer decides field visibility from hard-coded product-type arrays.
6 | Split NationalCode from rules | National-code records contain only official tariff data; country result resolution uses rules and official hierarchy.
7 | Add Chemicals + Raw materials domains | New domains are configured mostly with data; no dedicated hard-coded forms are introduced.
8 | Add regulations/taxes and national official ingestion | Country results show official code + restrictions + taxes + source/version.
9 | Staging/diff/publish imports | Official Excel/API/PDF imports never overwrite published history directly.
10 | Retire compatibility fields | After parity tests, deprecate IncisoNacional.cond/prio and hard-coded CAP_OK/ATTR metadata.

## Official_Data_Gaps
Area | Already in repository | Gap before calling it complete official data
Regional SAC | SIECA-derived 4/6-digit data, legal notes, ACI 10-digit source JSON and rebuild scripts. | Store publication/version/source/checksum in DB and model full hierarchy beyond only 4/6-digit PartidaSAC.
GT/SV/HN | ACI 10-digit lines are seeded for chapters present in motor_meta chapter map. | Current loader filters to the engine chapter set; ingest the complete desired chapter universe based on ChapterControl/dataset policy.
NI | Company/base national codes are present. | Load and version the current official Nicaragua national tariff/precisions and restrictions.
CR | Company/base national codes are present. | Ingest official ATENA/RIMM commodity, national notes and regulations with authenticated API access and validity dates.
PA | Company/base national codes are present. | Ingest current official Panama national tariff and later amendments; keep its national structure independent of MCCA assumptions.
Regulations | Legal basis text exists at country level; SAC legal notes exist. | Create row-level regulation/permit entities by national code/pattern and authority.
Taxes | Country-level impuesto text and DAI on national codes. | Separate tax rules from country metadata; version rates and legal basis.
Explanatory notes | Own summaries exist for selected headings. | Keep WCO official explanatory-note text external/licensed unless the organization has rights to store it.

## References
Reference | URL | Use
Repository | https://github.com/egcponcho/facturacion | Source repository reviewed
Working branch | https://github.com/egcponcho/facturacion/tree/claude/bold-lovelace-iwx2wa | Current branch reviewed; ahead of main
PR #18 | https://github.com/egcponcho/facturacion/pull/18 | Latest merged baseline into main before later branch commits
SIECA ACI | https://www.sieca.int/producto/arancel-centroamericano-de-importacion/ | Regional SAC source referenced by repository scripts
SAT Guatemala | https://portal.sat.gob.gt/portal/arancel-integrado/ | National tariff / permits source
DGA El Salvador | https://aduana2.mh.gob.sv/SAC/ | National SAC/tariff query
Aduanas Honduras | https://www.aduanas.gob.hn/ | National customs source
DGA Nicaragua | https://dgaweb.dga.gob.ni/sac01.cfm | National tariff query
ATENA Costa Rica | https://atena-test.hacienda.go.cr/es/custom-pages/informaci%C3%B3n-t%C3%A9cnica | RIMM/API documentation and tariff data
ANA Panamá | https://www.ana.gob.pa/w_ana/index.php/about-event/arancel-oficial-actualizado | Current national tariff publications